## Overview
Ascendus — Website Implementation Tracker
Source: Final Website Content, SEO, GEO & AEO Implementation Blueprint — issued for implementation, audit date 1 Sept 2026
Metric | Value
Live site score | 44 / 100
Projected score on implementation | 91 / 100
Live site audited | https://ascendus-website-dev.vercel.app/
Audit date | 1 September 2026
P0 findings (launch blockers) | 26
P1 findings | 20
Total implementation items (P0+P1) | 46
Content gap pages identified | 23
Redirects required (URL migration) | 22
Client information items required (Appendix A) | 15
Tracker progress (auto-updates from linked sheets)
Sheet | Total items | Done | In Progress | Not Started / Blocked | % Complete
P0 Launch Blockers | 26 | 3 | 6 | 17 | 1200%
P1 High Priority | 20 | 0 | 3 | 17 | 0%
URL Redirects | 22 | 0 | 0 | 22 | 0%
Content Gaps | 23 | 1 | 2 | 20 | 400%
Client Info Required | 15 | 0 | 0 | 15 | 0%
Priority roadmap (waves)
Wave | Timing | Scope | Gate condition
Wave 0 — Launch gate | Weeks 1–2 | C-001 to C-026 in full. Entity relationship resolved and legally approved. All placeholder metrics removed. Template-collision copy corrected. Locale switcher removed. Dev host noindexed. Robots and sitemap verified. | Nothing else starts until Wave 0 closes. No exceptions, no partial sign-off.
Wave 1 — Foundation | Weeks 3–6 | URL migration to /services/ with full redirect matrix. Per-route metadata. Organization/WebSite/Service/BreadcrumbList schema. Navigation rebuild. Homepage production copy. Case-study detail routes. | Depends on Wave 0. This is the point at which the site becomes indexable and measurable.
Wave 2 — Commercial depth | Weeks 7–14 | SAP hub plus S/4HANA and AMS. Microsoft hub plus Azure. Direct-answer blocks and FAQs on all P0 service pages. Proof registry populated. Author profiles and first six Insights articles. | Each page publishes only when its proof block is populated. A page with [PROOF REQUIRED] visible does not go live.
Wave 3 — Authority | Months 4–9 | Remaining SAP and Microsoft children. Industry pages, gated on referenceable engagements. Comparison guides. Trust centre. Leadership page. | Publication is gated on evidence, not on the calendar. A page with no proof waits.

## P0 Launch Blockers
P0 — Launch Blockers (26 items)
All P0 items must close before the site publishes. No partial sign-off. Owner + acceptance criteria per Sections 20 & 28 of the blueprint.
ID | Finding | Change required | Inferred implementation location | Owner | Wave | Status
C-001 | Canonical URL hard-coded site-wide to a foreign hostname | Replace the global canonical with a per-route self-referencing absolute canonical on the production host | Root layout metadata export / metadataBase | Frontend | Wave 0 | Done
C-002 | Identical browser title on every page | Per-route unique title from the metadata table (Section 10) | Per-route metadata export | SEO + Frontend | Wave 0 | Done
C-003 | Identical meta description on every page | Per-route unique meta description from the metadata table (Section 10) | Per-route metadata export | SEO + Frontend | Wave 0 | Done
C-004 | Open Graph / Twitter metadata global, pointing to an unresolved host | Per-route openGraph and twitter objects; og:url mirrors canonical; og:image on production host | Root layout + per-route metadata | SEO + Frontend | Wave 0 | Done
C-005 | Search Console verification placeholder shipped in production | Remove the google-site-verification placeholder | Root layout metadata | Frontend | Wave 0 | Not Started
C-006 | Obsolete meta keywords tag present | Remove the meta keywords tag | Root layout metadata | Frontend | Wave 0 | Done
C-007 | Placeholder proof metrics on the homepage (0+ counters) | Remove the four homepage counters; do not replace with estimates | Homepage stats component | Content + Frontend | Wave 0 | Not Started
C-008 | Placeholder proof metrics on the AI page (0+ / 0% counters) | Remove the four AI page counters; re-introduce only from the proof registry | AI page stats component | Content + Frontend | Wave 0 | Not Started
C-009 | Grammatical defects in homepage hero support copy | Replace hero support paragraph with approved copy (Section 18) | Homepage section 2 component | Content + Frontend | Wave 0 | Done
C-010 | Footer entity string malformed ("Ascendus Powder by...") | Replace with legally approved entity relationship wording — gated on A-01 | Global footer component | Legal + Content | Wave 0 | In Progress
C-011 | Footer links leave the Ascendus entity (isupportz.com / Instagram) | Remove isupportz.com and isupportz.official links | Global footer component | Content + Frontend | Wave 0 | Not Started
C-012 | Brand assets carry wrong alt text and link text ("SST Logo") | Logo alt to "Ascendus"; header link accessible name to "Ascendus — home" | Header + footer components | Frontend | Wave 0 | Done
C-013 | Cybersecurity copy published under a CRM heading | Replace CRM Strategy card body (Section 19.1) | CX page service data | Content | Wave 0 | Done
C-014 | Managed-services copy published under a CX heading | Replace "Why Partner With Us" sub-heading (Section 19.2) | CX page component | Content | Wave 0 | Not Started
C-015 | Service card set duplicated on the AI page (duplicate H2s) | Stop duplicating AI service card DOM nodes | AI page carousel component | Frontend | Wave 0 | Done
C-016 | Industry card set duplicated three times on the homepage | Stop duplicating homepage industry card DOM nodes | Homepage industries marquee component | Frontend | Wave 0 | Done
C-017 | Empty headings shipped on the AI page | Supply copy for each empty heading, or remove the headings | AI page content data | Content | Wave 0 | Not Started
C-018 | Case study cards are not navigable | Add case study detail routes and link the index cards | Case studies route + card component | Frontend + Content | Wave 0 | Done
C-019 | Unverified performance claims published as proof (60% rework / pen test) | Remove or substantiate claims with measurement basis + client consent | Case study content source | Content + Leadership | Wave 0 | Not Started
C-020 | Locale switcher offers markets that cannot be served | Remove the locale and language switcher entirely for launch | Header component | Product + Frontend | Wave 0 | Not Started
C-021 | Declared market and verifiable location conflict (GCC claim, India-only address) | Align declared markets with verifiable presence | Metadata, footer, contact content | Leadership + Content | Wave 0 | Not Started
C-022 | Typographical defect in homepage capability card ("longterm") | Correct "longterm" to "long-term" in the Execution Discipline card | Homepage capability card data | Content | Wave 0 | Done
C-023 | No structured data detected | Implement Organization, WebSite, Service and BreadcrumbList JSON-LD | Root layout + per-route schema components | Frontend + SEO | Wave 0 | Done
C-024 | Robots and sitemap state unverified | Verify and publish robots.txt and sitemap.xml | robots and sitemap route handlers | Frontend + SEO | Wave 0 | Done
C-025 | Whitepapers surface published with no assets | Noindex /whitepapers and remove it from the footer | Whitepapers route metadata + footer | SEO + Frontend | Wave 0 | Not Started
C-026 | Development host is indexable | Noindex or access-restrict the *.vercel.app dev host | Deployment configuration | DevOps | Wave 0 | Not Started

## P1 High Priority
P1 — High Priority (20 items)
Sequenced into Waves 1–3 behind the Wave 0 launch gate. Owners per Section 20.2 of the blueprint.
ID | Finding / change required | Owner | Status
C-027 | Primary navigation omits Industries, Insights and Case Studies — proof and authority content is orphaned in the footer | Product + Frontend | Not Started
C-028 | Capability URLs use a camelCase /whatWeDo/ directory inconsistent with the recommended /services/ taxonomy | Product + Frontend | Won't Do — /whatWeDo/ retained (product decision 2026-09-03)
C-029 | /contact-us and /bookacall are non-standard slugs; CTA label inconsistent ("Book a Call" vs "Book a Consultation") | Product + Frontend | Not Started
C-030 | Live nav label "Business Advisory" conflicts with the approved service name "Transformation Advisory" | Product + Frontend | Not Started
C-031 | Slug /enterprise-transformation-practice contains internal organisational term ("practice") with no buyer/search value | Product + Frontend | Done
C-032 | No SAP hub or SAP sub-service pages exist, despite SAP being the primary commercial category | Product + Frontend | Done — content at /whatWeDo/ (no /services/ migration)
C-033 | No Microsoft hub or Microsoft platform pages exist, despite Microsoft partner status held by parent org | Product + Frontend | Done — content at /whatWeDo/ (no /services/ migration)
C-034 | Four industries presented on homepage with no destination pages — CTA resolves to /who-we-are | Product + Frontend | Not Started
C-035 | Homepage H1 requires a decision against the approved brand promise (Section 6) | Product + Frontend | Not Started
C-036 | Homepage carries two adjacent sections making near-identical breadth claims | Product + Frontend | Not Started
C-037 | No breadcrumb UI or BreadcrumbList schema on any page | Product + Frontend | Not Started
C-038 | No direct-answer blocks on any service page — no self-contained citable definitions for AI systems | Product + Frontend | In Progress
C-039 | Insights content has no attributable author entities, bios or author routes | Product + Frontend | Not Started
C-040 | No proof registry exists — every metric on the site is currently unowned and unsourced | Product + Frontend | Not Started
C-041 | CTA wording inconsistent and mostly non-specific ("Book a Call", "See What We Do", etc.) | Product + Frontend | Not Started
C-042 | Contact does not route by buying intent (new engagement / existing client / partnership / careers / media) | Product + Frontend | Not Started
C-043 | No deliberate internal linking between capability pages, case studies and insights | Product + Frontend | Not Started
C-044 | Majority of images on audited pages carry empty alt attributes | Product + Frontend | Done
C-045 | Homepage "Find Your Industry Solution" CTA resolves to /who-we-are, which has no industry content | Product + Frontend | Not Started
C-046 | No enterprise proof surfaces: no client logos, no named leadership, no certifications, no partner tier statements | Product + Frontend | Not Started

## URL Redirects
URL Migration — Redirect Matrix (22 routes)
Every legacy URL gets exactly one 301. No chains. No internal links left pointing at a redirecting URL. Sequence: canonical/metadata fix (Wave 0) -> migration (Wave 1) -> internal link rewrite -> sitemap regeneration -> submission.
Current URL | Final URL | Action | Canonical | Sitemap | Status
/whatWeDo/enterprise-transformation-practice | /services/enterprise-transformation/ | 301 | Self-referencing on target | Include target only | Won't Do (services rename) — but camelCase fixed: /whatWeDo/ renamed to kebab-case /what-we-do/ (2026-09-03), kept "What We Do" branding per product decision, not renamed to /services/
/whatWeDo/artificial-intelligence | /services/artificial-intelligence/ | 301 | Self-referencing on target | Include target only | Won't Do (services rename) — but camelCase fixed: /whatWeDo/ renamed to kebab-case /what-we-do/ (2026-09-03), kept "What We Do" branding per product decision, not renamed to /services/
/whatWeDo/cloud-infrastructure | /services/cloud-infrastructure/ | 301 | Self-referencing on target | Include target only | Won't Do (services rename) — but camelCase fixed: /whatWeDo/ renamed to kebab-case /what-we-do/ (2026-09-03), kept "What We Do" branding per product decision, not renamed to /services/
/whatWeDo/data-intelligence | /services/data-intelligence/ | 301 | Self-referencing on target | Include target only | Won't Do (services rename) — but camelCase fixed: /whatWeDo/ renamed to kebab-case /what-we-do/ (2026-09-03), kept "What We Do" branding per product decision, not renamed to /services/
/whatWeDo/digital-engineering | /services/digital-engineering/ | 301 | Self-referencing on target | Include target only | Won't Do (services rename) — but camelCase fixed: /whatWeDo/ renamed to kebab-case /what-we-do/ (2026-09-03), kept "What We Do" branding per product decision, not renamed to /services/
/whatWeDo/customer-experience | /services/customer-experience/ | 301 | Self-referencing on target | Include target only | Won't Do (services rename) — but camelCase fixed: /whatWeDo/ renamed to kebab-case /what-we-do/ (2026-09-03), kept "What We Do" branding per product decision, not renamed to /services/
/whatWeDo/experience-design | /services/experience-design/ | 301 | Self-referencing on target | Include target only | Won't Do (services rename) — but camelCase fixed: /whatWeDo/ renamed to kebab-case /what-we-do/ (2026-09-03), kept "What We Do" branding per product decision, not renamed to /services/
/whatWeDo/intelligent-automation | /services/intelligent-automation/ | 301 | Self-referencing on target | Include target only | Won't Do (services rename) — but camelCase fixed: /whatWeDo/ renamed to kebab-case /what-we-do/ (2026-09-03), kept "What We Do" branding per product decision, not renamed to /services/
/whatWeDo/cybersecurity-digital-trust | /services/cybersecurity-digital-trust/ | 301 | Self-referencing on target | Include target only | Won't Do (services rename) — but camelCase fixed: /whatWeDo/ renamed to kebab-case /what-we-do/ (2026-09-03), kept "What We Do" branding per product decision, not renamed to /services/
/whatWeDo/managed-services | /services/managed-services/ | 301 | Self-referencing on target | Include target only | Won't Do (services rename) — but camelCase fixed: /whatWeDo/ renamed to kebab-case /what-we-do/ (2026-09-03), kept "What We Do" branding per product decision, not renamed to /services/
/whatWeDo/business-advisory | /services/transformation-advisory/ | 301 — includes service rename | Self-referencing on target | Include target only | Won't Do (services rename) — but camelCase fixed: /whatWeDo/ renamed to kebab-case /what-we-do/ (2026-09-03), kept "What We Do" branding per product decision, not renamed to /services/
/whatWeDo/innovation-emerging-technologies | /services/innovation/ | 301 | Self-referencing on target | Include target only | Won't Do (services rename) — but camelCase fixed: /whatWeDo/ renamed to kebab-case /what-we-do/ (2026-09-03), kept "What We Do" branding per product decision, not renamed to /services/
/contact-us | /contact/ | 301 | Self-referencing on target | Include target only | Done — redirects to /contact, all internal links updated, verified live
/bookacall | /book-a-consultation/ | 301 | Self-referencing on target | Include target only | Done — redirects to /book-a-consultation, all internal links updated, verified live
/who-we-are | /who-we-are/ | 301 — trailing-slash normalisation | Self-referencing on target | Include target only | Done — sitewide trailing-slash convention enabled (trailingSlash: true), verified live: single-hop 308 redirect to /who-we-are/
/blog | /insights/ | 301 — includes section rename | Self-referencing on target | Include target only | Won't Do — product decision: keep /blog as-is, not renaming to /insights
/whitepapers | — (retain, do not redirect) | Noindex + unlink now; publish when first 3 assets exist | n/a | Exclude | N/A — premise outdated: /whitepapers now has 6 real published whitepapers (Supabase-backed), not empty as the blueprint assumed. Noindex/unlink recommendation no longer applies.
/termsOfService | /legal/terms/ | 301 — camelCase legal routes normalised | Self-referencing on target | Include target only | Done — redirects to /legal/terms, all internal links updated, verified live
/privacyPolicy | /legal/privacy/ | 301 | Self-referencing on target | Include target only | Done — redirects to /legal/privacy, all internal links updated, verified live
/securityPrivacyPolicy | /legal/security/ | 301 | Self-referencing on target | Include target only | Done — redirects to /legal/security, all internal links updated, verified live
/cookiePolicy | /legal/cookies/ | 301 | Self-referencing on target | Include target only | Done — redirects to /legal/cookies, all internal links updated, verified live
/?service=* (if resolvable) | Parent service page | 301 + noindex — dev to confirm if routes still exist | Self-referencing on target | Include target only | Won't Do — /whatWeDo/ retained, no /services/ migration (product decision 2026-09-03)

## Content Gaps
Content Gaps — Missing Pages (23 items)
Each page has a distinct search intent and a commercial or evidential job. Publication is gated on evidence per the roadmap (Section 27) — a page with no proof waits.
Priority | Proposed page | URL | Intent | Reason | Wave | Status
P0 | SAP Services hub | /services/sap/ | Vendor evaluation | SAP is the lead term in the site title and the primary commercial category. It currently has no destination. | Wave 2 | Not Started
P0 | SAP S/4HANA | /services/sap/s4hana/ | Solution discovery | Highest-value commercial search intent in the portfolio. | Wave 2 | Not Started
P0 | SAP Application Management Services | /services/sap/ams/ | Vendor evaluation | Transactional intent; the service most likely to be searched by name during a vendor shortlist. | Wave 2 | Not Started
P1 | RISE with SAP | /services/sap/rise-with-sap/ | Solution discovery | Distinct buying decision with independent search demand. | Wave 3 | Not Started
P1 | GROW with SAP | /services/sap/grow-with-sap/ | Solution discovery | Distinct from S/4HANA; different buyer profile. | Wave 3 | Not Started
P1 | SAP BTP | /services/sap/btp/ | Technical evaluation | Clean-core extension is the question every S/4HANA evaluator asks second. | Wave 3 | Not Started
P1 | SAP SuccessFactors | /services/sap/successfactors/ | Vendor evaluation | Separate buying centre (HR, not IT). | Wave 3 | Not Started
P1 | Microsoft Services hub | /services/microsoft/ | Vendor evaluation | Microsoft partner status is held; there is no page that says so. | Wave 2 | Not Started
P1 | Microsoft Azure | /services/microsoft/azure/ | Solution discovery | Platform-specific intent that Cloud & Infrastructure should not absorb. | Wave 2 | Not Started
P1 | Power Platform | /services/microsoft/power-platform/ | Solution discovery | Owns Microsoft low-code intent; keeps Intelligent Automation platform-neutral. | Wave 3 | Not Started
P1 | Dynamics 365 | /services/microsoft/dynamics-365/ | Vendor evaluation | [CLIENT VALIDATION REQUIRED] — publish only if delivery capability is verified. | Wave 3 | Not Started
P1 | Power BI | /services/microsoft/power-bi/ | Solution discovery | [CLIENT VALIDATION REQUIRED] — publish only if delivery capability is verified. | Wave 3 | Not Started
P1 | Industries index | /industries/ | Problem exploration | Four industries are named on the homepage with no destination; the CTA currently resolves to /who-we-are. | Wave 3 | Not Started
P1 | Manufacturing | /industries/manufacturing/ | Problem exploration | Named on the homepage. Publish only with at least one referenceable engagement. | Wave 3 | Not Started
P1 | Financial Services | /industries/financial-services/ | Problem exploration | Named on the homepage. Regulatory content must be reviewed before publication. | Wave 3 | Not Started
P1 | Government & Public Sector | /industries/public-sector/ | Problem exploration | Named on the homepage. Compliance claims require validation. | Wave 3 | Not Started
P1 | Retail & Distribution | /industries/retail-distribution/ | Problem exploration | Named on the homepage. | Wave 3 | Not Started
P1 | Case study detail routes | /case-studies/[slug]/ | Vendor evaluation | Three case studies exist with no navigable detail page (C-018). | Wave 1 | Done
P1 | Author profiles | /insights/authors/[slug]/ | Due diligence | Required for credible Article/Person entity relationships and for E-E-A-T. | Wave 2 | Not Started
P2 | Services index | /services/ | Solution exploration | A single parent that defines the taxonomy and distributes link equity to twelve children. | Wave 1 | Not Started
P2 | Trust and security centre | /trust/ | Due diligence | Consolidates security posture, data handling and compliance for procurement review. | Wave 3 | In Progress
P2 | Leadership | /who-we-are/leadership/ | Due diligence | Named, attributable leadership is the cheapest available E-E-A-T improvement. | Wave 3 | Not Started
P3 | Comparison guides | /insights/guides/[slug]/ | Solution exploration | e.g. SLA-based vs capacity-based vs outcome-based AMS models. High AEO value. | Wave 3 | Not Started

## Client Info Required
Appendix A — Client Information Required (15 items)
A-01 is a launch blocker; the remainder gate specific pages or claims. Nothing here should be estimated, inferred, or filled with a plausible-sounding figure.
ID | Information required | Where it appears | Why it matters | Blocker? | Status
A-01 | Corporate relationship between Ascendus and Support Studio Technologies | Footer, About page, Organization schema, legal pages, social profiles | LAUNCH BLOCKER. Every entity, GEO and trust recommendation depends on it. Nothing publishes until legal confirms the exact wording. | Yes | Not Started
A-02 | Legal entity names, registration numbers and registered addresses (India and any GCC entity) | Legal pages, About, Organization schema, Contact | Required for Organization schema and for procurement due diligence. | No | Not Started
A-03 | GCC presence — is there a KSA or UAE entity, address or registered office? | Metadata, Contact, About, Industries | Site currently claims GCC focus with no GCC address. Either substantiate it or change the market claim (C-021). | No | Not Started
A-04 | Technology partner statuses and tiers (SAP, Microsoft, Salesforce, Databricks, MuleSoft) | Homepage, SAP hub, Microsoft hub, About | SAP partner logo is displayed in the header. Specific status must be confirmed before it stays. | No | Not Started
A-05 | Certifications held and number of certified practitioners | Proof blocks, SAP pages, About | Replaces the removed 0+ counters. Publish only exact, current, evidenced figures. | No | Not Started
A-06 | Headcount, engagement count, industries served, years operating | Homepage proof block | The four removed homepage counters. Each needs an owner and a measurement date. | No | Not Started
A-07 | Client logo display permissions | Homepage, case studies, About | Required before any logo wall is built. | No | Not Started
A-08 | Case-study metrics — 60% rework reduction and zero-critical-findings pen test result | /case-studies and detail routes | Both are specific, quantified and attributable. Need measurement basis and written client consent, or publish qualitatively/anonymously (C-019). | No | Not Started
A-09 | Whether case-study work was delivered as Ascendus or as Support Studio Technologies | Case studies | Currently attributed to Ascendus. If the brand is new, attribution needs a defensible form of words. | No | Not Started
A-10 | Verified capability scope per platform — SAP module coverage, Microsoft stack, Salesforce, Databricks | All service and platform pages | Determines which of the conditional pages in the blueprint are permitted to publish at all. | No | Not Started
A-11 | Managed services coverage windows, SLA commitments, languages and delivery locations | Managed Services, SAP AMS | Cannot describe an AMS offering credibly without these. | No | Not Started
A-12 | Named subject-matter experts willing to author Insights, with bios and photographs | Insights, author routes, About | Required for E-E-A-T and for the Article/Person schema relationships. | No | Not Started
A-13 | Current open roles, employing entity and work locations | Careers, JobPosting schema | JobPosting markup requires an accurate hiring organisation and location. | No | Not Started
A-14 | Confirmation of which markets are genuinely served | Locale handling, metadata, Industries | Determines whether any locale or hreflang implementation is justified (C-020). | No | Not Started
A-15 | Security, privacy and compliance claims the organisation can evidence | Security policy, trust centre | Unverifiable control claims are a procurement liability, not a differentiator. | No | Not Started