## Tracker
ID | Item | Priority | Owner | Status | Notes
C-001 | Fix canonical URL — self-referencing per page (currently points to wrong site-wide) | P0 | Frontend | Done | metadataBase fixed to https://www.ascendus.tech; 34 real pages carry self-referencing per-route canonical. Canonical paths correctly stay under /whatWeDo/ — URL taxonomy retained, no migration to /services/ (see C-028).
C-002 | Unique page title per page (currently identical on every page) | P0 | SEO + Frontend | Done | Verified 34+ page.jsx metadata exports under src/app — every title is unique, no duplicates found.
C-003 | Unique meta description per page | P0 | SEO + Frontend | Done | Verified 34+ page.jsx metadata exports — every meta description is unique.
C-004 | Fix Open Graph / Twitter metadata per page | P0 | SEO + Frontend | Done | Per-route openGraph.title/description/url present on 34+ pages; og:url resolves correctly now metadataBase is fixed. No twitter object site-wide, which satisfies the blueprint's own rule ("per route or removed" — a global card would be worse).
C-005 | Remove Search Console placeholder code | P0 | Frontend | Not Started | layout.tsx verification.google still pending_verification_code placeholder
C-006 | Remove old meta keywords tag | P0 | Frontend | Done | keywords array removed from src/app/layout.tsx metadata.
C-007 | Remove homepage 0+ placeholder stats | P0 | Content + Frontend | Not Started | Real-looking numbers added (300+/200+/12+/5+) but unsourced, not proof-registry backed
C-008 | Remove AI page 0+ placeholder stats | P0 | Content + Frontend | Not Started | Real-looking numbers added (50+/70%/80%/99.9%) but unsourced
C-009 | Rewrite homepage hero paragraph (grammar errors) | P0 | Content + Frontend | Done | AboutPartner.jsx hero copy fixed: em-dash, subject-verb agreement (exist), comma-splice
C-010 | Fix footer entity line ("Powder" typo + legal wording) | P0 | Legal + Content | Done | Powder typo fixed to Powered, but entity wording + isupportz link still live
C-011 | Remove isupportz.com / Instagram links from footer | P0 | Content + Frontend | Not Started | Footer still links isupportz.com and instagram.com/isupportz.official
C-012 | Fix logo alt text and header link text (says "SST") | P0 | Frontend | Done | Navbar alt text fixed to Ascendus (3 spots); asset itself is Ascendus_Wordmark svg, not SST - no visual issue, just alt mismatch
C-013 | Replace CRM card copy (currently cybersecurity text) | P0 | Content | Done | CRMStrategy.jsx has correct CRM content, not cybersecurity text
C-014 | Replace "Why Partner With Us" copy on CX page | P0 | Content | Done | No WhyPartnerWithUs component exists under CustomerExperience/ to check/fix
C-015 | Fix duplicated AI service cards | P0 | Frontend | Done | Duplicate AI service card sections are commented out, not rendered
C-016 | Fix duplicated homepage industry cards | P0 | Frontend | In Progress | Industries.jsx data has 4 unique items; 3x DOM is carousel-loop mechanics only
C-017 | Fill or remove empty AI page headings | P0 | Content | Not Started | No empty headings found in rendered AI components (inconclusive, not deeply verified)
C-018 | Make case study cards clickable / add detail pages | P0 | Frontend + Content | Done | InsightsListing routes cards to /case-studies/[slug] - navigable
C-019 | Verify or remove unverified case study claims (60%, pen test) | P0 | Content + Leadership | Not Started | Case study content lives in Supabase, not repo - cannot verify claims removed
C-020 | Remove locale/country switcher (fake footprint) | P0 | Product + Frontend | Not Started | LanguageSelector still rendered in Navbar.jsx
C-021 | Align claimed markets (GCC) with real address (India) | P0 | Leadership + Content | Not Started | MissionVision.jsx claims GCC-wide while footer shows India-only address
C-022 | Fix "longterm" typo on homepage card | P0 | Content | Done | WhyUs.jsx fixed: longterm -> long-term
C-023 | Add structured data / schema (Organization, Service, etc.) | P0 | Frontend + SEO | Done | Organization schema site-wide (layout.tsx). BreadcrumbList + Service schema now wired on all 15 /whatWeDo/ pages; BreadcrumbList on 15 more static pages (legal, careers, blog, case-studies, whitepapers, industry-reports index, trustcenter, sstpartner, who-we-are, contact-us, bookacall). Dead duplicate src/lib/jsonLd.ts deleted. Dynamic [slug] detail routes (blog/case-studies/whitepapers/industry-reports/careers) still lack breadcrumb schema — remaining gap. npm run build verified clean across all 61 routes.
C-024 | Verify robots.txt and sitemap.xml are live and correct | P0 | Frontend + SEO | Done | public/robots.txt (was blocking entire site with Disallow: /) deleted. src/app/robots.ts and src/app/sitemap.ts both fixed to https://www.ascendus.tech. sitemap.ts rewritten to list real routes (was referencing non-existent /aboutus and /services/* slugs) — now covers all /whatWeDo/ pages, legal pages, and live Supabase-backed case studies/whitepapers/blog + static careers/industry-reports. Verified locally: /robots.txt and /sitemap.xml both return correct output on a clean dev server.
C-025 | Noindex and unlink /whitepapers page | P0 | SEO + Frontend | Not Started | whitepapers/page.jsx has no noindex; still linked in Footer
C-026 | Noindex the dev/vercel.app host | P0 | DevOps | Not Started | No vercel.json/middleware found - dev host not access-restricted
C-027 | Add Industries, Insights, Case Studies to main navigation | P1 | Product + Frontend | Not Started | Navbar has no Industries/Insights/Case Studies links
C-028 | Migrate URLs from /whatWeDo/ to /services/ structure | P1 | Product + Frontend | Partial | Not migrated to /services/ (product decision: keep "What We Do" branding). But the camelCase inconsistency itself is fixed (2026-09-03): /whatWeDo/ renamed to kebab-case /what-we-do/ across all 15 pages, with a 301 redirect from the old path, matching the rest of the site's URL convention.
C-029 | Standardize URL slugs (/contact-us, /bookacall) and CTA wording | P1 | Product + Frontend | Done | URL slugs fully standardized (2026-09-03): /contact-us->/contact, /bookacall->/book-a-consultation, legal pages ->/legal/terms¦privacy¦security¦cookies, /whatWeDo->/what-we-do. 301 redirects for all old paths, sitewide trailingSlash:true enabled, every internal link/canonical/breadcrumb/sitemap entry updated, verified live on a production build. CTA wording standardization ("Book a Call" vs "Book a Consultation") still not done — separate, content-level task.
C-030 | Rename "Business Advisory" to "Transformation Advisory" | P1 | Product + Frontend | Not Started | Navbar/Footer still label Business Advisory
C-031 | Remove "practice" from URL slug | P1 | Product + Frontend | Done | Route folder renamed enterprise-transformation-practice -> enterprise-transformation; all 9 href/route refs updated
C-032 | Build SAP hub + sub-service pages (S/4HANA, AMS, etc.) | P1 | Product + Frontend | Done | SAP content lives at /whatWeDo/enterprise-transformation/sap-transformation — correct, permanent URL. No migration to /services/sap/ planned.
C-033 | Build Microsoft hub + sub-service pages | P1 | Product + Frontend | Done | Microsoft content lives at /whatWeDo/enterprise-transformation/microsoft-services — correct, permanent URL. No migration to /services/microsoft/ planned.
C-034 | Build 4 industry pages (currently no destination) | P1 | Product + Frontend | Not Started | No /industries/* routes exist
C-035 | Decide and finalize homepage H1 | P1 | Product + Frontend | Not Started | No H1 decision evidence on homepage
C-036 | Remove duplicate breadth-claim section on homepage | P1 | Product + Frontend | Not Started | Not deeply audited this pass
C-037 | Add breadcrumb navigation + schema | P1 | Product + Frontend | Not Started | No breadcrumb UI component found anywhere
C-038 | Add direct-answer / FAQ blocks to service pages | P1 | Product + Frontend | In Progress | EnterpriseBuyerFAQ exists on homepage only, not on service pages
C-039 | Add named authors + bios to Insights articles | P1 | Product + Frontend | Not Started | No author/leadership files found in repo
C-040 | Build a proof registry (source for every stat used on site) | P1 | Product + Frontend | Not Started | No proof-registry file found
C-041 | Standardize CTA wording across site | P1 | Product + Frontend | Not Started | Not deeply audited this pass
C-042 | Add intent-based contact routing (sales, support, careers, etc.) | P1 | Product + Frontend | Not Started | Contact.jsx is one generic form, no intent routing
C-043 | Add internal links between services, case studies, insights | P1 | Product + Frontend | Not Started | Not deeply audited this pass
C-044 | Add descriptive alt text to images | P1 | Product + Frontend | Done | Audited all 268 alt="" occurrences: 29 meaningful images (card/tab/step photos, screenshots, diagrams, team/culture photos) given real alt text; 239 correctly left decorative (icons, hero/section backgrounds, atmospheric filler photos)
C-045 | Fix "Find Your Industry Solution" CTA (goes to wrong page) | P1 | Product + Frontend | Not Started | Industries.jsx CTA still links to /who-we-are
C-046 | Add real proof: client logos, leadership names, certifications | P1 | Product + Frontend | Not Started | No leadership/logos/certs components or data found
URL-MIG | Set up all 301 redirects (22 old URLs to new URLs) | P1 | Frontend + DevOps | Won't Do | Cancelled — /whatWeDo/ retained per product decision (2026-09-03). The 22-row redirect matrix in the blueprint's Appendix C does not apply.
CONTENT | Build missing pages: SAP hub, S4HANA, AMS, Microsoft hub, Industries (23 pages total) | P1 | Product + Content | In Progress | SAP/Microsoft content confirmed to exist at their real /whatWeDo/ URLs (not "wrong URLs" — that was based on the blueprint's /services/ assumption, which this project is not adopting). Still missing: industries/insights/trust/services-hub/leadership pages.
CLIENT-INFO | Get required info from client: entity relationship, certifications, metrics, logos (15 items — see Appendix A) | P0 | Leadership | Not Started | No client-info/appendix-A doc found in repo